## Sprint 1-Discovery
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-2 As a CagoChat app user, I should be able to discover other CagoChat users within range, so I can request connection with them in order to do messaging | 1. CGCHAT-14 Discovery mode On starting up the CagoChat app, it should do two things automatically: a) Turn on and advertise WiFi direct functionality on this device b) Discover nearby available WiFi direct devices Use WifiP2pManager class for discovery peers. This should be existing functionality in wifidirect demo code from Google. Once a number of devices have been discovered, they should be displayed on the GUI, with their "device" name (the friendly name will come later, in Sprint # 2). The name should be clickable. On choosing to click the name, a connection request will be initiated. | Not Started |  |  | 0% | 2
Sprint # 1, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014
CagoChat
CagoChat
Android device
Android device
CagoChat
CagoChat
Android device
Android device
Both users start app
Android device
Android device
Scanning
Scanning
When app starts, it automatically turns on Wi-Fi Direct and scans for nearby users. We should save the user from “button clicks”, where it is obvious. Otherwise, we have to provide explanation for the function of buttons.
Android device
Android device
John
Jane
Jane
Doe
Keep refreshing every 5 sec
In Sprint # 1, we won’t implement the user friendly name. We will keep it simple and go with the default device name in settings.
Android device
Android device
John
Jane
Jane
Doe
First time, the second user is prompted whether they want to accept connection. After that, it is remembered.

## Sprint 2-Connection
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-4 As a CagoChat app user, I should be able to establish connection with other CagoChat users after I have discovered them, so I can perform messaging with them | 1. CGCHAT-15 WifiP2pManager->Connect Assumption is that CagoChat app has been started and peer CagoChat users have been discovered and displayed on the GUI. Clicking on a peer CagoChat user should establish a connection with that user. Use WifiP2PManager->Connect for connect selected peer public void connect(WifiP2pConfig config) { manager.connect(channel, config, new ActionListener() This has been implemented in wifi direct demo code by Google | Not Started |  |  | 0% | 2
Sprint # 1, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014
Android device
Android device
John
Doe
Connecting to Doe …
Connecting to John … Accept connection question first time?
Android device
Android device
y
hi
hi
y
y
y
END
END

## Sprint 3
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-3 As a CagoChat app user, I should be able to identify myself to other app users using a friendly name like "Rohit", so they know who is requesting connection with them | 1. CGCHAT-12 As a developer, I want to implement a gui to change the wifi direct device name >>Implement a GUI to present to user to be able to change the device name. 2. CGCHAT-13 As a developer, I want to integrate the gui to change the device name to CagoChat gui >>Integrate the functionality of changing the device name in CagoChat GUI. 3. CGCHAT-17 Find out SDK function to rename group name Provide interface to modify device name >>will create GUI and call back function to connect to exiting sdk api | Not Started |  |  | 0% | 2
Sprint # 2, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014

## Sprint 4
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-21 As a CagoChat app user, I should be able to click a button to terminate the connection with a user, so that I am no longer connected to them over Wi-Fi direct | 1. CGCHAT-21 Disconnect | Not Started |  |  | 0% | 2
Sprint # 2, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014
Android device
Android device
y
hi
hi
y
y
y
END
END
Either user can click End to stop the chat session
Android device
Android device
Scanning
Scanning
Android device
Android device
John
Jane
Jane
Doe
Keep refreshing every 5 sec

## Sprint 5
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-20 As a CagoChat user, I should be notified when connection errors happen, so that I am aware of what has gone wrong and what are the next steps |  | Not Started |  |  | 0% | 2
Sprint # 2, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014

## Sprint 6
User Story | Sub-Task | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
CGCHAT-23 As CagoChat app, I should be able to re-connect automatically with the second user, if the connection is broken but was not initiated via disconnect by user If the connection with second user is broken due to some reason, then the Connection Manager should try to reconnect automatically provided the second user is within range, and provided the disconnect was not initiated by the user |  | Not Started |  |  | 0% | 2
Sprint # 2, Epic # 1 - As a CagoChat app user, I should be able to message with other CagoChat users, using Wi-Fi direct (CGCHAT-1)
2014